## BurnPlan
	FPA 2025 Burn Plan

Issue	Desc	Total	Start	End	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
112	Payment to Kurt for improved infrastructure performance #112	4,800
248	Research Variant Parts #248 Hijma	8,000
247	Improve C++ API Documentation #247 Hijma	8,000
286	8000 EUR to Pieter Hijma for VarSet UX Improvement	8,000
287	1500 EUR Grant to kadet1090 for Unified Transparent Previews	1,500
288	1750 USD to Obelisk for icon design	1,750
280	3000 USD Grant to reqrefusion re documentation	3,000
289	6000 USD grant to Dr. Rajeevlochana G. Chittawadigi	6,000
	Other one time grants

	FOSDEM 2025 Facilities	4,500	Jan	Mar	1,500	1,500	1,500
	FOSDEM 2025 Travel	6,000	Jan	Mar	2,000	3,000	1,000
	North American Meet Up (??)	0	Jul	Sep

100	Payment to Adrian for maintenance and release support #100	12,000	Jan	Dec	1,000	1,000	1,000	1,000	1,000	1,000	1,000	1,000
168	Monthly payment to Max Wilfinger for Bug Triage Project #168	12,000	Jan	Dec	1,000	1,000	1,000	1,000	1,000	1,000	1,000	1,000
217	Blog coordination grant #217 (Alex Prokoudine)	6,000	Jan	Dec	500	500	500	500	500	500	500	500
113	Payment to concretedog (Jo Hinchliffe) for blog content #113	7,200	Jan	Dec	600	600	600	600	600	600	600	600
116	Monthly Stipend for FPA Chair #116	5,000	Jan	Dec	417	417	417	417	417	417	417	417
	Add-on coordinator	6,000					500	500	500	500	500	500	500	500
	OpenCascade liaison	6,000					500	500	500	500	500	500	500	500	500
	Translation coordinator	5,000					417	417	417

	Ondsel Onward placeholder	40,000

	Grant program to be awarded in 2025	80,000	Mar	Dec			8,000	8,000	8,000	8,000	8,000	8,000	8,000	8,000

	Total Operations	230,750

	To Reserves	10,000					5,000					5,000

	Grand Total	240,750			7,017	8,017	14,017	12,517	17,517	12,517	12,517	12,517	12,517	17,934	12,934	12,934	152,955

	fees	10000

	Other one time grants
	Homebrew update grant #271 (ipatch)				1000
	Payment to Francisco Rosa for FPA grant 5 - furniture library #209				1000

## BurnActual
	FPA 2025 Burn Actual

Issue	Desc	Total	Start	End	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
112	Payment to Kurt for improved infrastructure performance #112	4,800	0	0
248	Research Variant Parts #248 Hijma	8,000	0	0			8,000
247	Improve C++ API Documentation #247 Hijma	8,000	0	0
286	8000 EUR to Pieter Hijma for VarSet UX Improvement	8,000	0	0
287	1500 EUR Grant to kadet1090 for Unified Transparent Previews	1,500	0	0
288	1750 USD to Obelisk for icon design	1,750	0	0
280	3000 USD Grant to reqrefusion re documentation	3,000	0	0	1,500
289	6000 USD grant to Dr. Rajeevlochana G. Chittawadigi	6,000	0	0
0	Other one time grants	0	0	0	2,000		1,845	2,000

0	FOSDEM 2025 Facilities	4,500	Jan	Mar	1,924	3815.59	0	583
0	FOSDEM 2025 Travel	6,000	Jan	Mar	2,610	1,407
0	North American Meet Up (??)	0	Jul	Sep
0		0	0	0
100	Payment to Adrian for maintenance and release support #100	12,000	Jan	Dec	1,000	1,000	1,000	1,000
168	Monthly payment to Max Wilfinger for Bug Triage Project #168	12,000	Jan	Dec	1,000	1,000	1,000	1,000	1,000
217	Blog coordination grant #217 (Alex Prokoudine)	6,000	Jan	Dec	500	500	500	500	500
113	Payment to concretedog (Jo Hinchliffe) for blog content #113	7,200	Jan	Dec	600	600	600	600	600
116	Monthly Stipend for FPA Chair #116	5,000	Jan	Dec	405	405	0	405	405
0	Add-on coordinator	6,000	0	0
0	OpenCascade liaison	6,000	0	0					500
0	Translation coordinator	5,000	0	0
0		0	0	0
0	Ondsel Onward placeholder	40,000	0	0
0		0	0	0
0	Grant program to be awarded in 2025	80,000	Mar	Dec
0		0	0	0
0	Total Operations	230,750	0	0
0		0	0	0
0	To Reserves	10,000	0	0
0		0	0	0
0	Grand Total	240,750	0	0	11,539	8,728	12,945	6,088	3,005	0	0	0	0	0	0	0

## BurnVar
	FPA 2025 Burn Variance

Issue	Desc	Total	Start	End	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
112	Payment to Kurt for improved infrastructure performance #112	4,800	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
248	Research Variant Parts #248 Hijma	8,000	0	0	$0	$0	-$8,000	$0	$0	$0	$0	$0	$0	$0	$0	$0
247	Improve C++ API Documentation #247 Hijma	8,000	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
286	8000 EUR to Pieter Hijma for VarSet UX Improvement	8,000	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
287	1500 EUR Grant to kadet1090 for Unified Transparent Previews	1,500	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
288	1750 USD to Obelisk for icon design	1,750	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
280	3000 USD Grant to reqrefusion re documentation	3,000	0	0	-$1,500	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
289	6000 USD grant to Dr. Rajeevlochana G. Chittawadigi	6,000	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	Other one time grants	0	0	0	-$2,000	$0	-$1,845	-$2,000	$0	$0	$0	$0	$0	$0	$0	$0
					$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	FOSDEM 2025 Facilities	4,500	Jan	Mar	-$424	-$2,316	$1,500	-$583	$0	$0	$0	$0	$0	$0	$0	$0
0	FOSDEM 2025 Travel	6,000	Jan	Mar	-$610	$1,593	$1,000	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	North American Meet Up (??)	0	Jul	Sep	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0		0	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
100	Payment to Adrian for maintenance and release support #100	12,000	Jan	Dec	$0	$0	$0	$0	$1,000	$1,000	$1,000	$1,000	$1,000	$1,000	$1,000	$1,000
168	Monthly payment to Max Wilfinger for Bug Triage Project #168	12,000	Jan	Dec	$0	$0	$0	$0	$0	$1,000	$1,000	$1,000	$1,000	$1,000	$1,000	$1,000
217	Blog coordination grant #217 (Alex Prokoudine)	6,000	Jan	Dec	$0	$0	$0	$0	$0	$500	$500	$500	$500	$500	$500	$500
113	Payment to concretedog (Jo Hinchliffe) for blog content #113	7,200	Jan	Dec	$0	$0	$0	$0	$0	$600	$600	$600	$600	$600	$600	$600
116	Monthly Stipend for FPA Chair #116	5,000	Jan	Dec	$12	$12	$417	$12	$12	$417	$417	$417	$417	$417	$417	$417
0	Add-on coordinator	6,000	0	0	$0	$0	$0	$500	$500	$500	$500	$500	$500	$500	$500	$500
0	OpenCascade liaison	6,000	0	0	$0	$0	$0	$500	$0	$500	$500	$500	$500	$500	$500	$500
0	Translation coordinator	5,000	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$417	$417	$417
0		0	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	Ondsel Onward placeholder	40,000	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0		0	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	Grant program to be awarded in 2025	80,000	Mar	Dec	$0	$0	$8,000	$8,000	$8,000	$8,000	$8,000	$8,000	$8,000	$8,000	$8,000	$8,000
0		0	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	Total Operations	230,750	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0		0	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	To Reserves	10,000	0	0	$0	$0	$0	$0	$5,000	$0	$0	$0	$0	$5,000	$0	$0
0		0	0	0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0
0	Grand Total	240,750	0	0	-$4,522	-$711	$1,072	$6,429	$14,512	$12,517	$12,517	$12,517	$12,517	$17,934	$12,934	$12,934

## Graph
FPA 2025 Burn Plan Summary
	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
Planned Spending	$7,017	$8,017	$14,017	$12,517	$17,517	$12,517	$12,517	$12,517	$12,517	$17,934	$12,934	$12,934
Actual Spending	$11,539	$8,728	$12,945	$6,088	$3,005	$0	$0	$0	$0	$0	$0	$0
Variance	-$4,522	-$711	$1,072	$6,429	$14,512	$0	$0	$0	$0	$0	$0	$0
Burn Summary April 2025